## hidar
h
Labor utilization Hidar- 2018
Item No | Type of Labour | Type of work | Project
|  |  | Mehal Sayint |  |  | Sayint Adjibar
|  |  | Used | Required (as per the standard) | Percent usage | Used | Required (as per the standard) | Percent usage | Used | Required (as per the standard) | Percent usage
| Mason | concrete work - For ring beam -500m3 | 1 | 0.11 | 909.0909
|  | Apply three coats of plaster in cement mortar to internal cement concrete block wall | 3 | 0.69 | 434.7826
|  | Rendering to external cement concrete block wall including plastering of external smooth concrete wall and parfait HCB wall above roof cover. | 6 | 1.17 | 512.8205
|  | 30mm cement screed for floor | 2 | 0.33 | 606.0606
|  | Provide and construct 1.90m *1.90m stone masonry valve chamber as per the drawing. Price including 4mm thick sheet metal and excavation, hard core and finishing works of valve chamber | 6.92 | 0.99 | 698.9899
|  | Provide and construct 2.7m *2.4m stone masonry valve chamber as per the drawing. Price including 4mm thick sheet metal and excavation, hard core and finishing works of valve chamber. | 3.08 | 3.05 | 100.9836
|  | Construction of RCC class C-25 for pipe encasement for road, River, Gully and Road crossings as per standard drawings, price includes excavation, reinforcement, formwork, backfill and any other necessary works. | 1 | 0.45 | 222.2222
1 |  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 150cm to a height of 2.3m above ground level with 7 lines of barbed wire mesh of 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm. | 12 | 0.04 | 3000000%
Total sum
4 | D.Labor | Prepare and provide as built drawings of all works constructed under this contract as per the specification and to the satisfaction of engineer or client (Including the existing system) |  | 0.4 | 0
2*1.2m*1.2m and 5*1.5*1.2 metal sheet double opening windows (1.5mm thick) with suitable hinges and lock and key system approved by the Engineer.
|  | 1.2m*1.2m | 1 | 0.11 | 909.0909
|  | 1.5m*1.2m | 1.5 | 0.99 | 151.5152
4*0.8m*2.1m one open and 2*1.2*2.1 double open metal sheet doors (1.5mm thick) with suitable hinges and lock and key system approved by the Engineer.
|  | 0.8m*2.1m | 2 | 2 | 100
|  | 1.2m*2.1m | 1 | 1 | 100
|  | Construct 4000mmx2000mm size gate with metal frame and rectangular hollow tube RHS 100mm*100mm*3mm including 2mm sheet metal having three coats of antirust painting, including hinges and lock. | 3
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 150cm to a height of 2.3m above ground level with 7 lines of barbed wire mesh of 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm. | 27 | 12.76
Installation HDPE Compression Reducer (mmxmm),PN10
|  | OD 63*50 | 0.5 | 0.2 | 250
|  | OD 63*40 | 0.5 | 0.2 | 250
|  | OD160mm Stub Flange Adaptors | 2 | 1.6 | 125
|  | OD200*110*200 butt weld reducer Tee | 0.5 | 0.53 | 94.3396
|  | OD63*63*63 Butt weld | 0.5 | 0.4 | 125
|  | OD75*75*75 Butt weld | 0.5 | 0.4 | 125
|  | OD63*2" female adapter | 2 | 0.8 | 250
1 1/4" GI nipples
|  | 1 1/2" GI nipple | 0.5 | 0.22 | 227.2727
|  | 2" GI nipple | 5.5 | 5.33 | 103.1895
|  | 2 1/2" GI nipple | 5 | 4.8 | 104.1667
|  | 2" GI union | 2 | 2.13 | 93.8967
|  | 2 1/2" GI union | 1 | 1.07 | 93.4579
|  | Threaded Gate valve DN2" | 1 | 1.07 | 93.4579
|  | Install Double Flanged Pressure Reduce Valve (PRV) DN 150mm PN10 Q=29.05 l/s to be installed on OD160mm PN10 Pipe; the PRV should reduce an Inlet Pressure of 62.72 m H2O/6.3 Bar/ to an Outlet pressure of 20m H2O /2Bar/ under flow Condition (for Dynamic Pressure Control) and Reduce an Inlet pressure of 80.14 m H2O /8.01Bar/ to an Outlet pressure of 20m H2O /2Bar/ under the No flow Condition (for Static Pressure Control) i.e the Pressure should have a) "dropping -tight controlling future. The PRV should contain the important components such as balanced spring Diaphragm, Valve Fittings like stainless steel strainer, any another necessary Works. | 0.5 | 0.53 | 94.3396
|  | OD160mm Butt Weld Stub Flanged Adapter with backing ring | ` | 1.07
|  | OD200mm x OD160 Butt Weld Reducer , PN10 | 0.5 | 0.53 | 94.3396
|  | DN150 Dismantling joint PN10 | 0.5 | 0.53 | 94.3396
|  | DN150mm Double Flanged CI Gate Valve, PN10 | 0.5 | 0.8 | 62.5
For PRV-2
|  | Install Double Flanged Pressure Reduce Valve (PRV) DN50mm PN10 Q=2.65 l/s to be installed on OD63mm Pipe; the PRV should reduce an Inlet Pressure of 13.7 m H2O/1.4 Bar/ to an Outlet pressure of 10m H2O /1.0Bar/ under flow Condition (for Dynamic Pressure Control) and Reduce an Inlet pressure of 78.8 m H2O /7.9 Bar/ to an Outlet pressure of 10m H2O /1 Bar/ under the No flow Condition (for Static Pressure Control) i.e the Pressure should have a) "dropping -tight controlling future. The PRV should contain the important components such as balanced spring Diaphragm, Valve Fittings like stainless steel strainer, and any another necessary Works. | 0.5 | 0.53 | 94.3396
|  | DN80 Dismantling joint PN10 | 0.5 | 0.53 | 94.3396
|  | Double Flanged Pressure Reduce Valve (PRV) DN80mm PN10 Q=5.48 l/s to be installed on OD90mm Pipe; the PRV should reduce an Inlet Pressure of 48 m H2O/4.8 Bar/ to an Outlet pressure of 30m H2O /3.0Bar/ under flow Condition (for Dynamic Pressure Control) and Reduce an Inlet pressure of 78.8 m H2O /7.9 Bar/ to an Outlet pressure of 30m H2O /3 Bar/ under the No flow Condition (for Static Pressure Control) i.e the Pressure should have a) "dropping -tight controlling future. The PRV should contain the important components such as balanced spring Diaphragm, Valve Fittings like stainless steel strainer, and any another necessary Works. | 0.5 | 0.53 | 94.3396
|  | DN80mm Double Flanged CI Gate Valve, PN10 |  |  | #DIV/0!
|  | OD90mm Butt Weld Stub Flanged Adapter with backing ring,PN10 | 1 | 1.06 | 94.3396
|  | DN80 Dismantling joint PN10 | 0.5 | 0.53 | 94.3396
|  | Provide and construct 1.90m *1.90m stone masonry valve chamber as per the drawing. Price including 4mm thick sheet metal and excavation, hard core and finishing works of valve chamber | 42 | 37.13 | 113.1161
|  | Provide and construct 2.7m *2.4m stone masonry valve chamber as per the drawing. Price including 4mm thick sheet metal and excavation, hard core and finishing works of valve chamber. | 14 | 18.26 | 76.6703
|  | Construction of RCC class C-25 for pipe encasement for road, River, Gully and Road crossings as per standard drawings, price includes excavation, reinforcement, formwork, backfill and any other necessary works. | 10 | 17.53 | 57.0451
|  | concrete work - For ring beam -500m3 | 15 | 1.05 | 1428.5714
|  | formwork- For top beam -500m3 | 48 | 9.78 | 490.7975
|  | formwork- For ring beam -500m3 | 8 | 5.99 | 133.5559
|  | Diameter 20 mm deformed bar | 6 | 3.43 | 174.9271
|  | Diameter 16 mm deformed bar | 1.5 | 0.36 | 416.6667
|  | Diameter 12 mm deformed bar | 28 | 22.87 | 122.4311
|  | Diameter 10 mm deformed bar | 12 | 8.14 | 147.4201
|  | Diameter 8 mm deformed bar | 1.5 | 0.66 | 227.2727
|  | Supply and Installation of 2'' GS pipe ladder with safety gage and installation with 5.5 m height and horizontal member 1'' GI pipe width 50cm with spacing of ladder 30cm c/c for internal part as shown the drawing and hooked to base and roof slabs. | 1 | 0.17 | 588.2353
#DIV/0!
|  | 1.5mm thick sheet metal doors, size 2.00 x 1.00m | 1 | 1 | 100
Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 100cm to a height of 2.3m above ground level with 7 lines of barbed wire mesh of 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm.
|  | Construct 1500mmx2000mm size gate with metal frame and rectangular hollow tube RHS 40*40 mm with 3 mm thickness including 2mm thickness sheet metal having three coats of antirust painting including hinges and lock. | 5 | 5 | 100
|  | Supply and fix 900mm x 2100 mm metal door 1.5 mm thick Ribbed sheet metal price including hinges and lock. | 2 | 2 | 100
|  | Supply and fix 1200mm x 1200 mm metal frame 1.5 mm thick Ribbed sheet metal window price including hinges and lock | 1
|  | Apply three coats of plaster in cement mortar to internal cement concrete block wall | 3 | 2.48 | 120.9677
|  | Rendering to external cement concrete block wall including plastering of external smooth concrete wall and parfait HCB wall above roof cover. | 6 | 2.34 | 256.4103
|  | 30mm cement screed for floor | 2 | 0.66 | 303.0303
|  | GS 4” pipe - for vent pipe -500m3 | 1 | 0.1 | 1000
|  | GS 4” Tee - for vent pipe -500m3 | 1 | 1.6 | 62.5
|  | Trench excavation Depth up to 80cm and width up to 60cm.(By Labour) |  |  |  | 22.5 | 35.71 | 63.01%
|  | Trench excavation Depth up to 80cm and width up to 60cm.(By Excavator) |  |  |  |  | 0.18 | 0%
Ditto but item no 1.1 Trench excavation depth up to 80cm and width up to 60cm
|  | a. Soft rock (by machine) |  |  |  | 49 | 0.19
|  | b. Hard rock (by machine) |  |  |  |  | 1.18 | 0%
|  | a. Soft rock (by labour) ( contrat) |  |  |  | 14 | 22.22 | 63.01%
|  | b. Hard rock (by labour) (contrat) |  |  |  | 20 | 53.33 | 37.5%
|  | Back fill with excavated soil (By Labour) |  |  |  | 4.5 | 19.72 | 22.82%
|  | PE100 PN10 OD63 HDPE -installation |  |  |  | 1 | 0.44 | 227.3%
|  | Bulk Excavation for foundation to depth not exceeding 500mm |  |  |  | 8 | 8.4 | 95.24%
|  | Ditto as item 1.1 but in soft rock |  |  |  | 11 | 12.96 | 84.88%
|  | HDPE PE 100 PN 25OD 280 mm - installation |  |  |  | 20 | 23.33 | 85.73%
|  | Tractor ( material transportation) sand,gravle &cement |  |  |  | 30
|  | ø 6 mm |  |  |  | 1 | 0.13 | 769.2%
Non Income Work
|  | hard rock excavation of pipe trench for road crossing | 5.4 | 21.6 | 25
ለ500ሜ.ኩ አርማታ ሙሌት ሚክስር ማዘጋጀት፣ጠጠር ለየሚክሰሩ ማስጠጋት መሰላል ማጠናከር
|  | Re excavation and back fill for valve chamber | 30 | 30.9 | 97.0874
ጠጠር ፣ድንጋይ እና አሽዋ የማጓጓዝ ስራ ለvalve chamber , ለRiver crossing and for fence።
500m3 አርማታ ስራ ቅድመ ዝግጅትና መሰላል ስራ
ከ 500ሜ/ኩ ታንከር ጣራ ፎርሞርክ እንጨት ማስገባት ስራ
|  | door fixing | 15 | 10 | 150
|  | window fixing | 7 | 1.54 | 454.5455
| Bar bender | overlap HDPE pipe welding
|  | Diameter 20 mm deformed bar | 3.47 | 1.14 | 304.386
|  | Diameter 16 mm deformed bar | 0.36 | 0.12 | 300
|  | Diameter 12 mm deformed bar | 22.52 | 7.6 | 296.3158
|  | Diameter 10 mm deformed bar | 8 | 2.71 | 295.203
|  | Diameter 8 mm deformed bar | 0.65 | 0.22 | 295.4545
|  | ø 6 mm |  |  |  | 1 | 0.06
|  | Provide and construct 1.90m *1.90m stone masonry valve chamber as per the drawing. Price including 4mm thick sheet metal and excavation, hard core and finishing works of valve chamber |  | 0.51 | 0
|  | Provide and construct 2.7m *2.4m stone masonry valve chamber as per the drawing. Price including 4mm thick sheet metal and excavation, hard core and finishing works of valve chamber. |  | 0.21 | 0
|  | Construction of RCC class C-25 for pipe encasement for road, River, Gully and Road crossings as per standard drawings, price includes excavation, reinforcement, formwork, backfill and any other necessary works. |  | 0.46 | 0
| carpenter | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 150cm to a height of 2.3m above ground level with 7 lines of barbed wire mesh of 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm. | 22
Construct 1500mmx2000mm size gate with metal frame and rectangular hollow tube RHS 80mm*80 mm with 3 mm thickness including sheet metal having three coats of antirust painting including hinges and lock.
2*1.2m*1.2m and 5*1.5*1.2 metal sheet double opening windows (1.5mm thick) with suitable hinges and lock and key system approved by the Engineer.
|  | 1.2m*1.2m | 1 | 0.33 | 303.0303
|  | 1.5m*1.2m | 1.5 | 0.66 | 227.2727
4*0.8m*2.1m one open and 2*1.2*2.1 double open metal sheet doors (1.5mm thick) with suitable hinges and lock and key system approved by the Engineer.
|  | 0.8m*2.1m | 2
|  | 1.2m*2.1m | 1
|  | Construct 4000mmx2000mm size gate with metal frame and rectangular hollow tube RHS 100mm*100mm*3mm including 2mm sheet metal having three coats of antirust painting, including hinges and lock. | 5
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 150cm to a height of 2.3m above ground level with 7 lines of barbed wire mesh of 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm. | 27 | 6.6 | 409.0909
|  | Construct 1500mmx2000mm size gate with metal frame and rectangular hollow tube RHS 80mm*80 mm with 3 mm thickness including sheet metal having three coats of antirust painting including hinges and lock. | 1
|  | Form Work for Top Slab | 48 | 14.67 | 327.1984
|  | For ring beam | 8 | 2.99 | 267.5585
|  | Supply and fix 900mm x 2100 mm metal door 1.5 mm thick Ribbed sheet metal price including hinges and lock. |  | 1 | 0
|  | Supply and fix 1200mm x 1200 mm metal frame 1.5 mm thick Ribbed sheet metal window price including hinges and lock | 2 | 1 | 200
door fixing
window fixing
|  | Provide and construct 1.90m *1.90m stone masonry valve chamber as per the drawing. Price including 4mm thick sheet metal and excavation, hard core and finishing works of valve chamber |  | 2.88
|  | Provide and construct 2.7m *2.4m stone masonry valve chamber as per the drawing. Price including 4mm thick sheet metal and excavation, hard core and finishing works of valve chamber. |  | 1.38
|  | Total sum | 2 | 1
Item No | Type of Labour | Type of work | Project
|  |  | Mehal Sayint |  |  | Sayint Adjibar
|  |  | Used | Required (as per the standard) | Percent usage | Used | Required (as per the standard) | Percent usage | Used | Required (as per the standard) | Percent usage
| Cement | concrete work - For ring beam -500m3 | 11 | 11.72 | 93.8567
|  | Provide and construct 1.90m *1.90m stone masonry valve chamber as per the drawing. Price including 4mm thick sheet metal and excavation, hard core and finishing works of valve chamber | 10.5 | 15.57
1 |  | Provide and construct 2.7m *2.4m stone masonry valve chamber as per the drawing. Price including 4mm thick sheet metal and excavation, hard core and finishing works of valve chamber. | 8 | 8.26
|  | Construction of RCC class C-25 for pipe encasement for road, River, Gully and Road crossings as per standard drawings, price includes excavation, reinforcement, formwork, backfill and any other necessary works. | 12 | 12.82
|  | Apply three coats of plaster in cement mortar to internal cement concrete block wall | 1.5 | 1.09 | 137.6147
|  | Rendering to external cement concrete block wall including plastering of external smooth concrete wall and parfait HCB wall above roof cover. | 5 | 0.72 | 694.4444
|  | 30mm cement screed for floor | 1 | 1.26 | 79.3651
|  | Total sum | #REF! | #REF! |  | 0 | 0
|  | concrete work - For ring beam -500m3 | 1.5 | 1.27 | 118.1102
4 | sand | Provide and construct 1.90m *1.90m stone masonry valve chamber as per the drawing. Price including 4mm thick sheet metal and excavation, hard core and finishing works of valve chamber | 2.5 | 1.88 | 132.9787
|  | Provide and construct 2.7m *2.4m stone masonry valve chamber as per the drawing. Price including 4mm thick sheet metal and excavation, hard core and finishing works of valve chamber. | 2 | 0.96 | 208.3333
|  | Construction of RCC class C-25 for pipe encasement for road, River, Gully and Road crossings as per standard drawings, price includes excavation, reinforcement, formwork, backfill and any other necessary works. | 1 | 1.83 | 54.6448
|  | Apply three coats of plaster in cement mortar to internal cement concrete block wall | 0.35 | 0.27 | 129.6296
|  | Rendering to external cement concrete block wall including plastering of external smooth concrete wall and parfait HCB wall above roof cover. | 1.5 | 0.26 | 576.9231
|  | 30mm cement screed for floor | 2.11 | 0.19 | 1110.5263
Total sum
|  | concrete work - For ring beam -500m3 | 2.5 | 2.11 | 118.4834
| gravel | Provide and construct 1.90m *1.90m stone masonry valve chamber as per the drawing. Price including 4mm thick sheet metal and excavation, hard core and finishing works of valve chamber | 3.5 | 3.29 | 106.383
|  | Provide and construct 2.7m *2.4m stone masonry valve chamber as per the drawing. Price including 4mm thick sheet metal and excavation, hard core and finishing works of valve chamber. | 2.5 | 1.75 | 142.8571
|  | Construction of RCC class C-25 for pipe encasement for road, River, Gully and Road crossings as per standard drawings, price includes excavation, reinforcement, formwork, backfill and any other necessary works. | 3.25 | 2.77 | 117.3285
Total sum
| Stone |  |  |  | #DIV/0!
Total sum

## tahsas
Tahsas /2018 Labor utilization
Item No | Type of Labour | Type of work | Project
|  |  | Mehal Sayint |  |  | Sayint Adjibar
|  |  | Used | Required (as per the standard) | Percent usage | Used | Required (as per the standard) | Percent usage | Used | Required (as per the standard) | Percent usage
| Mason | Concrete Work
|  | For Roof Slab | 5 | 4 | 125
|  | 15cm thick C-30 reinforced concrete in top slab | 1 | 0.8 | 125
|  | 30mm screed for top slab with 1:2 cement sand mix | 2 | 1.06 | 188.6792
|  | Applying 12mm thick 3- coats of plastering of internal masonary wall of the collection chamber with 1:2 cement sand mix | 0.64 | 0.64 | 100
|  | Pointing work for exposed External wallb1:2 Cement Mortar | 2.8 | 2.67 | 104.8689
|  | Supply and place 250mm thick (equivalent to hard basaltic stone) hardcore blinded with crushed aggregate | 1 | 0.77 | 129.8701
|  | Supply and place 250 mm thick hard trachyte stone hard core | 1.5 | 1.46 | 102.7397
|  | 7cm mm thick C10 lean concrete under the cattle trough | 0.18 | 0.18 | 100
|  | Supply and raise 350 mm high C20 concrete side walls above the ground level extended for 400 mm below the ground level as shown in the drawing | 0.35 | 0.35 | 100 | 4 | 3.47 | 115.2738
|  | 1.2mx1.2m masonry Valve chamber construction as shown in the drawing | 0.5 | 0.5 | 100
|  | 30mm thick sand and cement floor screed | 0.36 | 0.36 | 100
|  | Top tie beams | 0.06 | 0.02 | 300
|  | Column | 0.05 | 0.02 | 250
|  | 20 cm thick HCB "class C" bedded in cement mortar with (1:3) ratio. | 3 | 3.02 | 99.3377
|  | Stone dressing | 4 | 2.72 | 147.0588
1
Total sum
4 | D.Labor | Prepare and provide as built drawings of all works constructed under this contract as per the specification and to the satisfaction of engineer or client (Including the existing system) | 44 | 22 | 200
Fabricate and erect metallic project sign board for project identification including printing of the title and necessary project descriptions as per the engineer order or client interest
Installation HDPE Butt Weld (mmxmm),PN10
|  | OD200*160 | 0.5 | 0.53 | 94.3396
|  | OD160*125 | 0.5 | 0.53 | 94.3396
|  | OD125*110 | 0.5 | 0.53 | 94.3396
|  | OD110*90 | 1 | 0.8 | 125
|  | OD90*75 | 1 | 0.8 | 125
Installation HDPE Compression Reducer (mmxmm),PN10
|  | OD110*40 | 0.5 | 0.2 | 250
|  | OD 75*40 | 1 | 0.6 | 166.6667
|  | OD 63*40 | 0.5 | 0.2 | 250
|  | HDPE PE100 Stub Flange Adaptors | 1 | 1.6 | 62.5
|  | OD160mm | 1 | 120 | 0.83333
|  | Butt welding - OD63*63*63 | 0.5 | 0.4 | 125
|  | Installation HDPE PE100 PN Female adapter |  |  | #DIV/0!
|  | OD40*1 1/4" | 1 | 0.4 | 250
|  | OD50*1 1/2" | 0.5 | 0.2 | 250
|  | OD63*2" | 3 | 1.6 | 187.5
|  | OD75*2 1/2" | 4 | 2 | 200
|  | Compression end plug - OD40mm | 1 | 0.4 | 250
|  | Compression end plug - OD50mm | 1.5 | 0.8 | 187.5
|  | Installation Flanged CI Gate Valves, PN10 |  |  | #DIV/0!
|  | DN100mm | 0.5 | 0.8 | 62.5
|  | DN150mm | 0.5 | 0.8 | 62.5
|  | Installation threaded GI Gate Valves, PN10 |  |  | #DIV/0!
|  | Threaded Gate valve DN11/4" | 0.5 | 0.22 | 227.2727
|  | Threaded Gate valve DN2" | 2 | 2.13 | 93.8967
|  | Threaded Gate valve DN21/2" | 2.5 | 2.67 | 93.633
|  | Concrete Work |  |  | #DIV/0!
|  | For Roof Slab | 94 | 77.63 | 121.0872
#DIV/0!
|  | 15cm thick C-30 reinforced concrete in top slab | 24 | 15.89 | 151.0384
|  | Swan Zigba form work for slab foundation |  |  | #DIV/0!
|  | Ditto but top slab | 0.5 | 0.34 | 147.0588
|  | Ditto but top tie beam | 1.25 | 0.46 | 271.7391
|  | 6mm Dai.bar for ring beam | 0.5 | 0.41 | 121.9512
|  | 12mm dai. RC bar for roof slab | 3 | 3.04 | 98.6842 | 5.5 | 5.19 | 105.973
|  | 10mm dai. RC bar for bottom slab and ring beam | 0.5 | 0.44 | 113.6364
|  | DN100mm GS double flanged pipe L=1.5 m at centeral puddled |  | 0.11 | 0
|  | GS 2 1/2'' L=1.5m Threaded pipe with Puddle. |  | 0.05 | 0
|  | GS 2'' L=1.5m Threaded pipe with Puddle. |  | 0.04 | 0
|  | GS 3” pipe - vent pipe |  | 0.03 | 0
|  | 30mm screed for top slab with 1:2 cement sand mix | 2 | 4.27 | 46.8384
|  | Applying 12mm thick 3- coats of plastering of internal masonary wall of the collection chamber with 1:2 cement sand mix | 1.25 | 1.28 | 97.6562
|  | Pointing work for exposed External wallb1:2 Cement Mortar |  |  | #DIV/0!
|  | Pointing work for exposed External wallb1:2 Cement Mortar | 5.5 | 5.34 | 102.9963
|  | Supply and installation of 2'' GS pipe ladder with 3.15m height and horizontal member 1'' GS pipe with 40cm c/c and 1m height and 0.30m handle above top slab for external part as shown the drawing and hooked to base and roof slabs. | 1 | 0.17 | 588.2353
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 150cm to a height of 2.3m above ground level with 7 lines of barbed wire mesh of 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm | 8.5 | 8.6 | 98.8372
|  | Construct 1500mmx2000mm size gate with metal frame and rectangular hollow tube RHS 80mm*80mm with 3 mm thickness including sheet metal having three coats of antirust painting including hinges and lock. | 1 | 1 | 100
|  | Provide and fix wire mesh for ventilation | 3 | 0.5 | 600
|  | Bulk excavation for foundation to a depth not exceeding 500mm | 2 | 2.06 | 97.0874
|  | Supply and place 250mm thick (equivalent to hard basaltic stone) hardcore blinded with crushed aggregate | 2.5 | 2.3 | 108.6957
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 100cm to a height of 2.3m above ground level with 7 lines of barbed wire mesh of 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm. | 4.5 | 2.2 | 204.5455 | 20 | 20 | 100%
|  | Clearing, grubbing and romoving of top soil up to 20cm | 3.5 | 3.61 | 96.9529
|  | Bulk excavation in ordinary soil to a depth not greater than 1.5m | 13 | 7.8 | 166.6667
|  | Supply and place 250 mm thick hard trachyte stone hard core | 4.5 | 4.39 | 102.5057
|  | 7cm mm thick C10 lean concrete under the cattle trough | 3.25 | 3.26 | 99.6933
|  | Supply and raise 350 mm high C20 concrete side walls above the ground level extended for 400 mm below the ground level as shown in the drawing | 6.25 | 6.3 | 99.2063 | 62 | 62.58 | 99.07%
|  | Diam. 8 mm | 0.75 | 0.69 | 108.6957
|  | supply and fix in position sawn formwork | 4.5 | 3.64 | 123.6264 | 14.5 | 14.4 | 100.7%
|  | 1.2mx1.2m masonry Valve chamber construction as shown in the drawing | 2 | 2 | 100
|  | 30mm thick sand and cement floor screed | 0.75 | 0.72 | 104.1667
|  | Supply and erect 1500x2100mm gate of RHS 2.5 frame and 2mm metal sheet, complete with hinges and lock | 4.5 | 4.5 | 100
|  | Top tie beams | 2 | 0.24 | 833.3333
|  | Column | 1.5 | 0.2 | 750
|  | ø 10 mm | 0.62 | 0.75 | 82.6667
|  | ø 6 mm | 0.24 | 0.25 | 96
|  | 20 cm thick HCB "class C" bedded in cement mortar with (1:3) ratio. | 6 | 6.05 | 99.1736
|  | Lower & upper chord 120mm dia | 1 | 0.72 | 138.8889
|  | Diagonals and verticals 80mm dia | 0.5 | 0.34 | 147.0588
|  | GS 4'' Union |  | 0.8 | 0
HDPE OD50 mm Female adaptor, PN10
|  | 4'' GS Medium Class Pipe |  | 27.56 | 0
|  | GI union DN 100 PN16 |  | 0.8 | 0
|  | OD 90 PN10 |  | 2.78 | 0
|  | DN100mm CI Flanged Dismantling Joint, PN10 |  | 1.07 | 0
| Bar bender | HDPE Butweld OD180mm90 degree elbow |  | 1.07 | 0
|  | HDPE OD90 mm Stub Flange Adaptor with back ring, with nuts and bolts. |  | 0.4 | 0
|  | OD40mm pipe |  | 1.12 | 0
|  | OD63mm pipe |  | 2.29 | 0
|  | OD 75*40 |  | 0.4 | 0
|  | Trench excavation Depth up to 80cm and width up to 60cm.(By Labour) | 58 | 96.26 | 60.2535 | 58 | 96.26 | 60.25%
|  | a. Soft rock (by labour) ( contrat) |  |  |  | 9 | 13.33 | 67.52%
|  | b. Hard rock (by labour) (contrat) |  |  |  | 12 | 30 | 40%
|  | Back fill with excavated soil (By Labour) |  |  |  | 35 | 40 | 87.5%
|  | Class K9 DCI DN250mm pipe |  |  |  | 59
|  | HDPE PE 100 PN 25OD 280 mm |  |  |  | 84 | 76 | 110.5%
|  | Re-excavation work |  |  |  | 20 | 20.71 | 96.57%
|  | ø 6 mm |  |  |  | 2 | 1.22 | 163.9%
|  | a. Soft rock (by labour) ( not contrat work) |  |  |  | 63 | 98.44 | 64%
|  | b. Hard rock (by labour) (not contrat work) |  |  |  | 245 | 402.23 | 60.91%
|  | form work dismantling ( ) |  |  |  | 4.5
Non Income Work
|  | Stone dressing | 4 | 2.72 | 147.0588
|  | Re excavation and back fill for valve chamber | 60 | 61 | 98.3607
|  | ጠጠር ፣ድንጋይ እና አሽዋ የማጓጓዝ ስራ ለchlorine house, water point, cattle trouph and 25m3 slab concrete work | 155
|  | production of valv chamber cover by 3mm sheet metal | 2 | 2 | 100
|  | for chlorin house HCB moblization | 5 | 5.5 | 90.9091
|  | valv chamber cover fixiing | 2.5 | 2.5 | 100
door fixing
|  | window fixing | 0.25 | 0.22 | 113.6364
|  | overlap HDPE pipe welding | 72
|  | Diam. 8 mm | 0.75 | 0.69 | 108.6957
|  | ø 10 mm | 0.75 | 0.62 | 120.9677
|  | ø 6 mm | 0.25 | 0.24 | 104.1667
|  | ø 12 mm |  |  |  | 3 | 2.59 | 115.8%
| carpenter | Swan Zigba form work for slab foundation
|  | Ditto but top slab | 0.5 | 0.17 | 294.1176
|  | Ditto but top tie beam | 0.75 | 0.23 | 326.087
|  | Construct 1500mmx2000mm size gate with metal frame and rectangular hollow tube RHS 80mm*80mm with 3 mm thickness including sheet metal having three coats of antirust painting including hinges and lock. |  | 0.05 | 0
|  | Provide and fix wire mesh for ventilation |  | 0.02 | 0
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 100cm to a height of 2.3m above ground level with 7 lines of barbed wire mesh of 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm. | 2.2 | 2.2 | 100
|  | supply and fix in position sawn formwork | 2.19 | 1.82 | 120.3297 | 7.5 | 7.2 | 104.1667
|  | Supply and erect 1500x2100mm gate of RHS 2.5 frame and 2mm metal sheet, complete with hinges and lock |  | 0.23 | 0
|  | Top tie beams | 2 | 0.24 | 833.3333
|  | Column | 1.5 | 0.2 | 750
|  | Lower & upper chord 120mm dia | 0.38 | 0.38 | 100
|  | Diagonals and verticals 80mm dia | 0.19 | 0.19 | 100
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 100cm to a height of 2.3m above ground level with 7 lines of barbed wire mesh of 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm. |  |  |  | 10 | 10 | 100
|  | form work dismantling ( ) |  |  |  | 2
Total sum
| Tahsas/2018 | Material utilization
Item No | Type of Labour | Type of work | Project
|  |  | Mehal Sayint |  |  | Sayint Adjibar
|  |  | Used | Required (as per the standard) | Percent usage | Used | Required (as per the standard) | Percent usage | Used | Required (as per the standard) | Percent usage
| Cement | For Roof Slab | 101 | 106.87 | 94.5073
|  | 15cm thick C-30 reinforced concrete in top slab | 22 | 21.89 | 100.5025
1 |  | 30mm screed for top slab with 1:2 cement sand mix | 3 | 3.12 | 96.1538
|  | Applying 12mm thick 3- coats of plastering of internal masonary wall of the collection chamber with 1:2 cement sand mix | 1 | 0.62 | 161.2903
|  | Pointing work for exposed External wallb1:2 Cement Mortar | 2 | 2.12 | 94.3396
|  | 7cm mm thick C10 lean concrete under the cattle trough | 2.5 | 3.02 | 82.7815
|  | Supply and raise 350 mm high C20 concrete side walls above the ground level extended for 400 mm below the ground level as shown in the drawing | 10 | 9.92 | 100.8065 | 109 | 98.4 | 110.7724
|  | 1.2mx1.2m masonry Valve chamber construction as shown in the drawing | 0.85 | 0.86 | 98.8372
|  | 30mm thick sand and cement floor screed | 1 | 1.06 | 94.3396
|  | Top tie beams |  | 1.86 | 0
|  | Column | 2 | 1.52 | 131.5789
|  | 20 cm thick HCB "class C" bedded in cement mortar with (1:3) ratio. | 6.25 | 6.27 | 99.681
Total sum
|  | For Roof Slab | 9.7 | 8.04 | 120.6468
4 | sand | 15cm thick C-30 reinforced concrete in top slab | 2.11 | 1.65 | 127.8788
|  | 30mm screed for top slab with 1:2 cement sand mix | 1 | 0.61 | 163.9344
|  | Applying 12mm thick 3- coats of plastering of internal masonary wall of the collection chamber with 1:2 cement sand mix | 1.06 | 1 | 106
|  | Pointing work for exposed External wallb1:2 Cement Mortar |  | 0.35 | 0
|  | 7cm mm thick C10 lean concrete under the cattle trough | 1 | 0.69 | 144.9275
|  | Supply and raise 350 mm high C20 concrete side walls above the ground level extended for 400 mm below the ground level as shown in the drawing | 1.5 | 1.42 | 105.6338 | 14.5 | 14.09 | 102.9%
|  | 1.2mx1.2m masonry Valve chamber construction as shown in the drawing | 0.25 | 0.23 | 108.6957
|  | 30mm thick sand and cement floor screed |  | 0.23 | 0
|  | Top tie beams | 0.25 | 0.27 | 92.5926
|  | Column |  | 0.22 | 0
|  | 20 cm thick HCB "class C" bedded in cement mortar with (1:3) ratio. | 1.5 | 1.54 | 97.4026
Total sum
|  | For Roof Slab | 15.76 | 13.39 | 117.6998 | 21 | 21.24 | 98.87%
| gravel | 15cm thick C-30 reinforced concrete in top slab | 3.5 | 2.74 | 127.7372
|  | 7cm mm thick C10 lean concrete under the cattle trough | 1.5 | 1.31 | 114.5038
|  | Supply and raise 350 mm high C20 concrete side walls above the ground level extended for 400 mm below the ground level as shown in the drawing | 2 | 2.14 | 93.4579
|  | Top tie beams |  | 0.4 | 0
|  | Column | 0.5 | 0.33 | 151.5152
|  | C-20 Concrete |  |  |  | 21 | 21.24 | 98.87%
Total sum
| Stone | Supply and place 250mm thick (equivalent to hard basaltic stone) hardcore blinded with crushed aggregate | 1 | 0.91 | 109.8901
|  | Supply and place 250 mm thick hard trachyte stone hard core | 6 | 5.85 | 102.5641
Total sum

## Tir
Tir /2018 Labor utilization
Item No | Type of Labour | Type of work | Project
|  |  | Mehal Sayint |  |  | Sayint Adjibar
|  |  | Used | Required (as per the standard) | Percent usage | Used | Required (as per the standard) | Percent usage | Used | Required (as per the standard) | Percent usage
| Mason | Concrete Work
|  | C-20 concrete |  |  |  | 1 | 0.43 | 232.5581
|  | 3cm thick Cement scread for base and roof slab at the top | 4.9 | 4.83 | 101.4493
|  | Chizling at 500m3, 100m3 and existing water point | 20.96 | 20.96 | 100
|  | Supply and place 250 mm thick hard trachyte stone hard core | 0.25 | 0.2 | 125
|  | Three coats of plastering to internal walls of manhole, using 1:3 mortar | 0.5 | 0.32 | 156.25
|  | Pointing stone masonry wall of water point with rich mortar | 2.25 | 2.13 | 105.6338
|  | 30mm thick sand and cement floor screed | 1 | 0.92 | 108.6957
|  | Stone dressing | 5.5 | 3.63 | 151.5152
1
Total sum
4 | D.Labor | Supply and erect fence of 40mm*40mm*3mm angle iron stands c/c spaced at 100cm to a height of 2m above ground level with 6 lines of barbed wire 200mm and 400mm spacing the bottom 4 and upper 2 lines, respectively with cross diagonal & to a depth of 50cm embedded in concrete foundation of 200mm*200mm. |  |  |  | 24 | 25.6 | 93.75%
|  | Trench excavation Depth up to 80cm and width up to 60cm.(By Labour) |  |  |  | 19 | 19.36 | 98.14%
|  | Back fill with excavated soil (By Labour) |  |  |  | 20.44 | 18.5 | 110.5%
|  | Class K9 DCI DN250mm pipe |  |  |  | 94 | 112.94 | 83.23%
|  | Ø 12mm |  |  |  | 1 | 0.57 | 175.4%
|  | Sawn Zigba form work |  |  |  | 2 | 1.6 | 125%
|  | HDPE PE 100 PN 25OD 280 mm |  |  |  | 31 | 21.33 | 145.3%
|  | a. Soft rock (by labour) ( not contrat work) |  |  |  | 64.73 | 51 | 126.9%
|  | b. Hard rock (by labour) (not contrat work) |  |  |  | 97.67 | 81 | 120.6%
|  | form work dismantling ( ) |  |  |  | 0.5 | 0.4 | 125%
|  | curing work |  |  |  | 17
|  | C-20 concrete |  |  |  | 7.68 | 7.68 | 100%
|  | Prepare and provide as built drawings of all works constructed under this contract as per the specification and to the satisfaction of engineer or client (Including the existing system) | 51 | 15 | 340
|  | Trench excavation in ordinary soil for pipe line to a depth of 0.9m and a width of 60cm and disposal of surplus excavated material | 2.79 | 8.87 | 31.4543
|  | Re-fill and properly compaction of the excavated material with native Soil for all excavated depth | 0.93 | 1.66 | 56.0241
|  | OD63mm pipe installation | 0.25 | 0.19 | 131.5789
|  | OD40mm compression end plug | 1 | 0.4 | 250
|  | Construction of RCC class C-25 for pipe encasement for road, River, Gully and Road crossings as per standard drawings, price includes excavation, reinforcement, formwork, backfill and any other necessary works. | 10 | 10 | 100
|  | 3cm thick Cement scread for base and roof slab at the top | 9.5 | 14.5 | 65.5172
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 150cm to a height of 2.3m above ground level with 7 lines of barbed wire of 2.5mm thick, 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm | 24 | 11.8 | 203.3898
|  | Bulk excavation in ordinary soil to a depth not greater than 1.5m | 4 | 2.69 | 148.6989
|  | Supply and place 250 mm thick hard trachyte stone hard core | 0.5 | 2.44 | 20.4918
|  | Three coats of plastering to internal walls of manhole, using 1:3 mortar | 1 | 0.64 | 156.25
|  | Pointing stone masonry wall of water point with rich mortar | 7 | 4.26 | 164.3192
|  | 30mm thick sand and cement floor screed | 2 | 1.83 | 109.2896
|  | Supply & fix 3mm thick sheet metal 80cmX80cm access cover with 40X40mm angle iron frame latch and lock for reservoir manhole | 3 | 3 | 100
| Barebender | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 200cm to a height of 2.1m above ground level with 10lines of barbed wiremesh with cross diagonal & to a depth of 70cm embedded in concrete foundation of 300mm*150mm | 8 | 12.1 | 66.1157
|  | Supply and erect 1500x2100mm gate of RHS 2.5 frame and 2mm metal sheet, complete with hinges and lock | 1.5 | 1.5 | 100
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 100cm to a height of 2.3m above ground level with 7 lines of barbed wire mesh of 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm. | 8 | 3.8 | 210.5263
|  | hard rock excavation of pipe trench for road crossing | 4.05 | 21.6 | 18.75
|  | Stone dressing | 5.4 | 5.5 | 98.1818
Form work Dismantling at 500m3
|  | Re excavation and back fill for over lap | 60 | 64.3 | 93.3126
|  | valv chamber cover fixiing | 1.5 | 1.5 | 100
|  | door fixing | 3 | 3 | 100
|  | overlap HDPE pipe welding | 54.5 | 54.5 | 100
|  | formork dismantling for 25 m3 reservoier | 2 | 0.68 | 294.1176
|  | Ø 12mm |  |  |  | 0.5 | 0.28 | 178.6%
| carpenter | Supply and erect fence of 40mm*40mm*3mm angle iron stands c/c spaced at 100cm to a height of 2m above ground level with 6 lines of barbed wire 200mm and 400mm spacing the bottom 4 and upper 2 lines, respectively with cross diagonal & to a depth of 50cm embedded in concrete foundation of 200mm*200mm. |  |  |  | 13 | 12.6 | 103.1746
|  | Sawn Zigba form work |  |  |  | 1 | 0.8 | 125
|  | form work dismantling ( ) |  |  |  | 0.5 | 0.2 | 250
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 150cm to a height of 2.3m above ground level with 7 lines of barbed wire of 2.5mm thick, 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm | 11.8 | 11.8 | 100
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 200cm to a height of 2.1m above ground level with 10lines of barbed wiremesh with cross diagonal & to a depth of 70cm embedded in concrete foundation of 300mm*150mm | 12.1 | 12.1 | 100
|  | valv chamber cover fixiing | 1.25 | 1.25 | 100
|  | door fixing | 1.75 | 1.75 | 100
|  | formork dismantling for 25 m3 reservoier | 0.34 | 1 | 34
Total sum
| Tir/2018 | Material utilization
Item No | Type of Labour | Type of work | Project
|  |  | Mehal Sayint |  |  | Sayint Adjibar
|  |  | Used | Required (as per the standard) | Percent usage | Used | Required (as per the standard) | Percent usage | Used | Required (as per the standard) | Percent usage
| Cement | Supply and erect fence of 40mm*40mm*3mm angle iron stands c/c spaced at 100cm to a height of 2m above ground level with 6 lines of barbed wire 200mm and 400mm spacing the bottom 4 and upper 2 lines, respectively with cross diagonal & to a depth of 50cm embedded in concrete foundation of 200mm*200mm. |  |  |  | 7.5
|  | C-20 concrete |  |  |  | 12 | 12.1 | 0.99174
|  | Construction of RCC class C-25 for pipe encasement for road, River, Gully and Road crossings as per standard drawings, price includes excavation, reinforcement, formwork, backfill and any other necessary works. | 10 | 14.04 | 71.2251
|  | 3cm thick Cement scread for base and roof slab at the top | 20 | 22.19 | 90.1307
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 150cm to a height of 2.3m above ground level with 7 lines of barbed wire of 2.5mm thick, 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm | 28 | 28.01 | 99.9643
|  | Three coats of plastering to internal walls of manhole, using 1:3 mortar | 0.75 | 0.76 | 98.6842
|  | Pointing stone masonry wall of water point with rich mortar | 1.25 | 1.24 | 100.8065
|  | 30mm thick sand and cement floor screed | 2.5 | 2.69 | 92.9368
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 200cm to a height of 2.1m above ground level with 10lines of barbed wiremesh with cross diagonal & to a depth of 70cm embedded in concrete foundation of 300mm*150mm | 28 | 36.59 | 76.5236
|  | valv chamber cover fixiing | 0.75 | 0.75 | 100
door fixing
Total sum
4 | sand | Supply and erect fence of 40mm*40mm*3mm angle iron stands c/c spaced at 100cm to a height of 2m above ground level with 6 lines of barbed wire 200mm and 400mm spacing the bottom 4 and upper 2 lines, respectively with cross diagonal & to a depth of 50cm embedded in concrete foundation of 200mm*200mm. |  |  |  | 1.5
|  | C-20 concrete |  |  |  | 2 | 1.73 | 115.6%
|  | Construction of RCC class C-25 for pipe encasement for road, River, Gully and Road crossings as per standard drawings, price includes excavation, reinforcement, formwork, backfill and any other necessary works. | 2 | 1.51 | 132.4503
|  | 3cm thick Cement scread for base and roof slab at the top | 3 | 3.34 | 89.8204
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 150cm to a height of 2.3m above ground level with 7 lines of barbed wire of 2.5mm thick, 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm | 5.5 | 5.1 | 107.8431
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 200cm to a height of 2.1m above ground level with 10lines of barbed wiremesh with cross diagonal & to a depth of 70cm embedded in concrete foundation of 300mm*150mm | 6 | 5.23 | 114.7228
|  | valv chamber cover fixiing | 1 | 1 | 100
|  | door fixing | 0.5 | 0.5 | 100
|  | Three coats of plastering to internal walls of manhole, using 1:3 mortar | 0.18 | 0.25 | 72
|  | Pointing stone masonry wall of water point with rich mortar | 0.5 | 0.31 | 161.2903
|  | 30mm thick sand and cement floor screed | 1 | 0.59 | 169.4915
Total sum
| gravel | Supply and erect fence of 40mm*40mm*3mm angle iron stands c/c spaced at 100cm to a height of 2m above ground level with 6 lines of barbed wire 200mm and 400mm spacing the bottom 4 and upper 2 lines, respectively with cross diagonal & to a depth of 50cm embedded in concrete foundation of 200mm*200mm. |  |  |  | 2
|  | C-20 concrete |  |  |  | 3 | 2.61 | 114.9%
|  | Construction of RCC class C-25 for pipe encasement for road, River, Gully and Road crossings as per standard drawings, price includes excavation, reinforcement, formwork, backfill and any other necessary works. | 3.25 | 3.02 | 107.6159
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 150cm to a height of 2.3m above ground level with 7 lines of barbed wire of 2.5mm thick, 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm | 6.5 | 6.05 | 107.438
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 200cm to a height of 2.1m above ground level with 10lines of barbed wiremesh with cross diagonal & to a depth of 70cm embedded in concrete foundation of 300mm*150mm | 7 | 6.2 | 112.9032
Total sum
| Stone | Supply and place 250 mm thick hard trachyte stone hard core | 4 | 3.25 | 123.0769
Total sum