## Tir
Tir /2018 Labor utilization
Item No | Type of Labour | Type of work | Project
|  |  | Mehal Sayint |  |  | Sayint Adjibar
|  |  | Used | Required (as per the standard) | Percent usage | Used | Required (as per the standard) | Percent usage | Used | Required (as per the standard) | Percent usage
| Mason | Concrete Work
|  | C-20 concrete |  |  |  | 1 | 0.43 | 232.5581
|  | 3cm thick Cement scread for base and roof slab at the top | 4.9 | 4.83 | 101.4493
|  | Chizling at 500m3, 100m3 and existing water point | 20.96 | 20.96 | 100
|  | Supply and place 250 mm thick hard trachyte stone hard core | 0.25 | 0.2 | 125
|  | Three coats of plastering to internal walls of manhole, using 1:3 mortar | 0.5 | 0.32 | 156.25
|  | Pointing stone masonry wall of water point with rich mortar | 2.25 | 2.13 | 105.6338
|  | 30mm thick sand and cement floor screed | 1 | 0.92 | 108.6957
|  | Stone dressing | 5.5 | 3.63 | 151.5152
1
Total sum
4 | D.Labor | Supply and erect fence of 40mm*40mm*3mm angle iron stands c/c spaced at 100cm to a height of 2m above ground level with 6 lines of barbed wire 200mm and 400mm spacing the bottom 4 and upper 2 lines, respectively with cross diagonal & to a depth of 50cm embedded in concrete foundation of 200mm*200mm. |  |  |  | 24 | 25.6 | 93.75%
|  | Trench excavation Depth up to 80cm and width up to 60cm.(By Labour) |  |  |  | 19 | 19.36 | 98.14%
|  | Back fill with excavated soil (By Labour) |  |  |  | 20.44 | 18.5 | 110.5%
|  | Class K9 DCI DN250mm pipe |  |  |  | 94 | 112.94 | 83.23%
|  | Ø 12mm |  |  |  | 1 | 0.57 | 175.4%
|  | Sawn Zigba form work |  |  |  | 2 | 1.6 | 125%
|  | HDPE PE 100 PN 25OD 280 mm |  |  |  | 31 | 21.33 | 145.3%
|  | a. Soft rock (by labour) ( not contrat work) |  |  |  | 64.73 | 51 | 126.9%
|  | b. Hard rock (by labour) (not contrat work) |  |  |  | 97.67 | 81 | 120.6%
|  | form work dismantling ( ) |  |  |  | 0.5 | 0.4 | 125%
|  | curing work |  |  |  | 17
|  | C-20 concrete |  |  |  | 7.68 | 7.68 | 100%
|  | Prepare and provide as built drawings of all works constructed under this contract as per the specification and to the satisfaction of engineer or client (Including the existing system) | 51 | 15 | 340
|  | Trench excavation in ordinary soil for pipe line to a depth of 0.9m and a width of 60cm and disposal of surplus excavated material | 2.79 | 8.87 | 31.4543
|  | Re-fill and properly compaction of the excavated material with native Soil for all excavated depth | 0.93 | 1.66 | 56.0241
|  | OD63mm pipe installation | 0.25 | 0.19 | 131.5789
|  | OD40mm compression end plug | 1 | 0.4 | 250
|  | Construction of RCC class C-25 for pipe encasement for road, River, Gully and Road crossings as per standard drawings, price includes excavation, reinforcement, formwork, backfill and any other necessary works. | 10 | 10 | 100
|  | 3cm thick Cement scread for base and roof slab at the top | 9.5 | 14.5 | 65.5172
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 150cm to a height of 2.3m above ground level with 7 lines of barbed wire of 2.5mm thick, 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm | 24 | 11.8 | 203.3898
|  | Bulk excavation in ordinary soil to a depth not greater than 1.5m | 4 | 2.69 | 148.6989
|  | Supply and place 250 mm thick hard trachyte stone hard core | 0.5 | 2.44 | 20.4918
|  | Three coats of plastering to internal walls of manhole, using 1:3 mortar | 1 | 0.64 | 156.25
|  | Pointing stone masonry wall of water point with rich mortar | 7 | 4.26 | 164.3192
|  | 30mm thick sand and cement floor screed | 2 | 1.83 | 109.2896
|  | Supply & fix 3mm thick sheet metal 80cmX80cm access cover with 40X40mm angle iron frame latch and lock for reservoir manhole | 3 | 3 | 100
| Barebender | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 200cm to a height of 2.1m above ground level with 10lines of barbed wiremesh with cross diagonal & to a depth of 70cm embedded in concrete foundation of 300mm*150mm | 8 | 12.1 | 66.1157
|  | Supply and erect 1500x2100mm gate of RHS 2.5 frame and 2mm metal sheet, complete with hinges and lock | 1.5 | 1.5 | 100
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 100cm to a height of 2.3m above ground level with 7 lines of barbed wire mesh of 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm. | 8 | 3.8 | 210.5263
|  | hard rock excavation of pipe trench for road crossing | 4.05 | 21.6 | 18.75
|  | Stone dressing | 5.4 | 5.5 | 98.1818
Form work Dismantling at 500m3
|  | Re excavation and back fill for over lap | 60 | 64.3 | 93.3126
|  | valv chamber cover fixiing | 1.5 | 1.5 | 100
|  | door fixing | 3 | 3 | 100
|  | overlap HDPE pipe welding | 54.5 | 54.5 | 100
|  | formork dismantling for 25 m3 reservoier | 2 | 0.68 | 294.1176
|  | Ø 12mm |  |  |  | 0.5 | 0.28 | 178.6%
| carpenter | Supply and erect fence of 40mm*40mm*3mm angle iron stands c/c spaced at 100cm to a height of 2m above ground level with 6 lines of barbed wire 200mm and 400mm spacing the bottom 4 and upper 2 lines, respectively with cross diagonal & to a depth of 50cm embedded in concrete foundation of 200mm*200mm. |  |  |  | 13 | 12.6 | 103.1746
|  | Sawn Zigba form work |  |  |  | 1 | 0.8 | 125
|  | form work dismantling ( ) |  |  |  | 0.5 | 0.2 | 250
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 150cm to a height of 2.3m above ground level with 7 lines of barbed wire of 2.5mm thick, 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm | 11.8 | 11.8 | 100
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 200cm to a height of 2.1m above ground level with 10lines of barbed wiremesh with cross diagonal & to a depth of 70cm embedded in concrete foundation of 300mm*150mm | 12.1 | 12.1 | 100
|  | valv chamber cover fixiing | 1.25 | 1.25 | 100
|  | door fixing | 1.75 | 1.75 | 100
|  | formork dismantling for 25 m3 reservoier | 0.34 | 1 | 34
Total sum
| Tir/2018 | Material utilization
Item No | Type of Labour | Type of work | Project
|  |  | Mehal Sayint |  |  | Sayint Adjibar
|  |  | Used | Required (as per the standard) | Percent usage | Used | Required (as per the standard) | Percent usage | Used | Required (as per the standard) | Percent usage
| Cement | Supply and erect fence of 40mm*40mm*3mm angle iron stands c/c spaced at 100cm to a height of 2m above ground level with 6 lines of barbed wire 200mm and 400mm spacing the bottom 4 and upper 2 lines, respectively with cross diagonal & to a depth of 50cm embedded in concrete foundation of 200mm*200mm. |  |  |  | 7.5
|  | C-20 concrete |  |  |  | 12 | 12.1 | 0.99174
|  | Construction of RCC class C-25 for pipe encasement for road, River, Gully and Road crossings as per standard drawings, price includes excavation, reinforcement, formwork, backfill and any other necessary works. | 10 | 14.04 | 71.2251
|  | 3cm thick Cement scread for base and roof slab at the top | 20 | 22.19 | 90.1307
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 150cm to a height of 2.3m above ground level with 7 lines of barbed wire of 2.5mm thick, 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm | 30
|  | Three coats of plastering to internal walls of manhole, using 1:3 mortar | 0.75 | 0.76 | 98.6842
|  | Pointing stone masonry wall of water point with rich mortar | 1.25 | 1.24 | 100.8065
|  | 30mm thick sand and cement floor screed | 2.5 | 2.69 | 92.9368
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 200cm to a height of 2.1m above ground level with 10lines of barbed wiremesh with cross diagonal & to a depth of 70cm embedded in concrete foundation of 300mm*150mm | 30
|  | valv chamber cover fixiing | 0.75 | 0.75 | 100
door fixing
Total sum
4 | sand | Supply and erect fence of 40mm*40mm*3mm angle iron stands c/c spaced at 100cm to a height of 2m above ground level with 6 lines of barbed wire 200mm and 400mm spacing the bottom 4 and upper 2 lines, respectively with cross diagonal & to a depth of 50cm embedded in concrete foundation of 200mm*200mm. |  |  |  | 1.5
|  | C-20 concrete |  |  |  | 2 | 1.73 | 115.6%
|  | Construction of RCC class C-25 for pipe encasement for road, River, Gully and Road crossings as per standard drawings, price includes excavation, reinforcement, formwork, backfill and any other necessary works. | 2 | 1.51 | 132.4503
|  | 3cm thick Cement scread for base and roof slab at the top | 3 | 3.34 | 89.8204
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 150cm to a height of 2.3m above ground level with 7 lines of barbed wire of 2.5mm thick, 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm | 5.5
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 200cm to a height of 2.1m above ground level with 10lines of barbed wiremesh with cross diagonal & to a depth of 70cm embedded in concrete foundation of 300mm*150mm | 6
|  | valv chamber cover fixiing | 1 | 1 | 100
|  | door fixing | 0.5 | 0.5 | 100
|  | Three coats of plastering to internal walls of manhole, using 1:3 mortar | 0.18 | 0.25 | 72
|  | Pointing stone masonry wall of water point with rich mortar | 0.5 | 0.31 | 161.2903
|  | 30mm thick sand and cement floor screed | 1 | 0.59 | 169.4915
Total sum
| gravel | Supply and erect fence of 40mm*40mm*3mm angle iron stands c/c spaced at 100cm to a height of 2m above ground level with 6 lines of barbed wire 200mm and 400mm spacing the bottom 4 and upper 2 lines, respectively with cross diagonal & to a depth of 50cm embedded in concrete foundation of 200mm*200mm. |  |  |  | 2
|  | C-20 concrete |  |  |  | 3 | 2.61 | 114.9%
|  | Construction of RCC class C-25 for pipe encasement for road, River, Gully and Road crossings as per standard drawings, price includes excavation, reinforcement, formwork, backfill and any other necessary works. | 3.25 | 3.02 | 107.6159
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 150cm to a height of 2.3m above ground level with 7 lines of barbed wire of 2.5mm thick, 200mm and 400mm spacing, the bottom 5 and upper 2 lines, respectively with cross diagonal & to a depth of 60cm embedded in concrete foundation of 300mm*300mm | 10
|  | Supply and erect 50mm*50mm*3mm angle iron stands with c/c spaced at 200cm to a height of 2.1m above ground level with 10lines of barbed wiremesh with cross diagonal & to a depth of 70cm embedded in concrete foundation of 300mm*150mm | 8
Total sum
| Stone | Supply and place 250 mm thick hard trachyte stone hard core | 4 | 3.25 | 123.0769
Total sum